## DMRB
Unit | Status | Move_out | Ready_Date | DV | Move_in | DTBR | N/V/M | Insp | Insp_status | Paint | Paint_status | MR | MR_Status | HK | HK_Status | CC | CC_status | Assign | W_D | QC | P | B | U | Notes
Unit 7-07-0104 | Vacant ready | 2026-01-05 | 2026-01-23 | 70 | 2026-03-19 | -3 | SMI | 2026-01-06 | Done | 2026-01-07 | Done | 2026-01-08 | Done | 2026-01-13 | Done | 2026-01-14 | Done | Brad | yes | No | 7 | 07 | 0104
Unit 5-17-0207 | Vacant not ready | 2026-02-21 | 2026-03-01 | 23 | 2026-03-21 | -5 | SMI | 2026-02-23 | Done | 2026-02-24 | Scheduled | 2026-02-25 | Scheduled | 2026-03-02 | Scheduled | 2026-03-03 | Scheduled | Total | Yes | No | 5 | 17 | 0207
Unit 5-18-0125 | Vacant not ready | 2026-02-19 | 2026-03-05 | 25 | 2026-03-21 | -5 | SMI | 2026-02-20 | Done | 2026-02-23 | Scheduled | 2026-02-24 | Scheduled | 2026-02-27 | Scheduled | 2026-03-02 | Scheduled | Total | Yes | No | 5 | 18 | 0125
Unit 5-11-0106 | Vacant ready | 2025-12-04 | 2026-01-12 | 102 | 2026-03-24 | -8 | SMI | 2025-12-05 | Done | 2025-12-08 | Done | 2025-12-09 | Done | 2025-12-12 | Done | 2025-12-15 | Done | Total | Yes stack | No | 5 | 11 | 0106
Unit 5-01-0221 | Vacant ready | 2025-12-30 | 2026-01-16 | 76 | 2026-03-25 | -9 | SMI | 2025-12-31 | Done | 2026-01-01 | Done | 2026-01-02 | Done | 2026-01-07 | Done | 2026-01-08 | Done | Total | yes | No | 5 | 01 | 0221
Unit 8-01-2007 | On Notice | 2026-03-12 | 2026-03-26 | 4 | 2026-03-26 | -10 | SMI |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started | Michael |  | No | 8 | 01 | 2007
Unit 8-01-3096 | Vacant ready | 2026-01-08 | 2026-01-22 | 67 | 2026-03-27 | -11 | SMI | 2026-01-09 | Done | 2026-01-12 | Done | 2026-01-13 | Done | 2026-01-16 | Done | 2026-01-19 | Done | Michael | Yes stack | No | 8 | 01 | 3096
Unit 8-01-1048 | Vacant ready | 2026-01-29 | 2026-02-09 | 46 | 2026-03-27 | -11 | SMI | 2026-01-30 | Done | 2026-02-02 | Done | 2026-02-03 | Done | 2026-02-06 | Done | 2026-02-09 | Done | Michael | Yes | No | 8 | 01 | 1048
Unit 5-18-0145 | On Notice | 2026-03-16 | 2026-03-28 | 0 | 2026-03-28 | -12 | SMI |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started | Total |  | No | 5 | 18 | 0145
Unit 5-17-0204 | Vacant not ready | 2026-02-23 | 2026-03-07 | 21 | 2026-04-01 | -16 | SMI | 2026-02-24 | Scheduled | 2026-02-25 | Scheduled | 2026-02-26 | Scheduled | 2026-03-03 | Scheduled | 2026-03-04 | Scheduled | Total | Yes | No | 5 | 17 | 0204
Unit 5-18-0117 | Vacant not ready | 2025-11-24 | 2026-02-28 | 112 | 2026-04-01 | -16 | SMI | 2025-11-25 | Done | 2025-11-26 | Done | 2025-11-27 | Done | 2025-12-02 | Done | 2025-12-03 | Done | Total | yes | No | 5 | 18 | 0117 | [ISSUE:Wether ¦ weather storm freezes]
Unit 5-03-0227 | Vacant not ready | 2026-02-18 | 2026-02-28 | 26 | 2026-04-01 | -16 | SMI | 2026-02-19 | Done | 2026-02-20 | Scheduled | 2026-02-23 | Scheduled | 2026-02-26 | Scheduled | 2026-02-27 | Scheduled | Total | Yes | No | 5 | 03 | 0227 | [ISSUE:Wether ¦ weather storm freezes]
Unit 7-03-0218 | On Notice | 2026-03-22 | 2026-04-02 | -6 | 2026-04-03 | -18 | NOTICE + SMI |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started | Brad |  | No | 7 | 03 | 0218
Unit 8-01-2074 | On Notice | 2026-03-22 | 2026-04-02 | -6 | 2026-04-04 | -19 | NOTICE + SMI |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started | Michael |  | No | 8 | 01 | 2074
Unit 7-07-0208 | On Notice | 2026-03-22 | 2026-04-02 | -6 | 2026-04-04 | -19 | NOTICE + SMI |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started | Brad |  | No | 7 | 07 | 0208
Unit 5-13-0306 | On Notice | 2026-03-22 | 2026-04-02 | -6 | 2026-04-09 | -24 | NOTICE + SMI |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started | Total |  | No | 5 | 13 | 0306
Unit 5-03-0427 | On Notice | 2026-03-26 | 2026-04-06 | -10 | 2026-04-10 | -25 | NOTICE + SMI |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started | Total |  | No | 5 | 03 | 0427
Unit 5-18-0234 | On Notice | 2026-03-27 | 2026-04-10 | -11 | 2026-04-10 | -25 | NOTICE + SMI |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started | Total |  | No | 5 | 18 | 0234
Unit 7-11-0411 | On Notice | 2026-03-22 | 2026-04-02 | -6 | 2026-04-11 | -26 | NOTICE + SMI |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started | Brad |  | No | 7 | 11 | 0411
Unit 5-02-0305 | On Notice | 2026-03-29 | 2026-04-09 | -13 | 2026-04-11 | -26 | NOTICE + SMI |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started | Total |  | No | 5 | 02 | 0305
Unit 5-14-0206 | On Notice | 2026-03-30 | 2026-04-11 | -14 | 2026-04-11 | -26 | NOTICE + SMI |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started | Total |  | No | 5 | 14 | 0206
Unit 5-13-0207 | On Notice | 2026-03-26 | 2026-04-09 | -10 | 2026-04-17 | -32 | NOTICE + SMI |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started | Total |  | No | 5 | 13 | 0207
Unit 7-07-0109 | On Notice | 2026-03-22 | 2026-04-02 | -6 | 2026-04-18 | -33 | NOTICE + SMI |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started | Brad |  | No | 7 | 07 | 0109
Unit 5-18-0413 | On Notice | 2026-04-10 | 2026-04-24 | -25 | 2026-04-24 | -39 | NOTICE + SMI |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started | Total |  | No | 5 | 18 | 0413
Unit 7-11-0213 | On Notice | 2026-04-10 | 2026-04-24 | -25 | 2026-04-24 | -39 | NOTICE + SMI |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  |  | No | 7 | 11 | 0213
Unit 5-15-0204 | On Notice | 2026-03-22 | 2026-04-02 | -6 | 2026-04-25 | -40 | NOTICE + SMI |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started | Total |  | No | 5 | 15 | 0204
Unit 7-07-0203 | On Notice | 2026-04-13 | 2026-04-25 | -28 | 2026-04-25 | -40 | NOTICE + SMI |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  |  | No | 7 | 07 | 0203
Unit 8-01-1119 | On Notice | 2026-04-11 | 2026-04-25 | -26 | 2026-04-25 | -40 | NOTICE + SMI |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started | Michael |  | No | 8 | 01 | 1119
Unit 5-11-0102 | On Notice | 2026-04-16 | 2026-04-23 | -31 | 2026-04-30 | -45 | NOTICE + SMI |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started | Total |  | No | 5 | 11 | 0102
Unit 8-01-1044 | On Notice |  |  |  | 2026-05-01 | -46 | [14 empty] | 8 | 01 | 1044
Unit 8-01-3082 | On Notice | 2026-03-22 | 2026-04-02 | -6 | 2026-05-02 | -47 | NOTICE + SMI |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started | Michael |  | No | 8 | 01 | 3082
Unit 5-18-0421 | On Notice | 2026-04-19 | 2026-05-02 | -34 | 2026-05-02 | -47 | NOTICE + SMI |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started | Total |  | No | 5 | 18 | 0421
Unit 7-08-0208 | On Notice | 2026-04-20 | 2026-05-02 | -35 | 2026-05-02 | -47 | NOTICE + SMI |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  |  | No | 7 | 08 | 0208
Unit 5-16-0201 | On Notice | 2026-04-27 | 2026-05-09 | -42 | 2026-05-09 | -54 | NOTICE + SMI |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started | Total |  | No | 5 | 16 | 0201
Unit 8-01-4008 | On Notice | 2026-03-22 | 2026-04-02 | -6 | 2026-05-16 | -61 | NOTICE + SMI |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started | Michael |  | No | 8 | 01 | 4008
Unit 5-12-0102 |  |  |  |  | 2026-05-16 | -61 | [14 empty] | 5 | 12 | 0102
Unit 8-01-4110 | On Notice | 2026-04-14 | 2026-04-28 | -29 | 2026-05-23 | -68 | NOTICE + SMI |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started | Michael |  | No | 8 | 01 | 4110
Unit 8-01-4091 | On Notice | 2026-05-09 | 2026-05-23 | -54 | 2026-05-23 | -68 | NOTICE + SMI |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  |  | No | 8 | 01 | 4091
Unit 7-02-0305 |  |  |  |  | 2026-05-28 | -73 | [14 empty] | 7 | 02 | 0305
Unit 5-02-0107 | On Notice | 2026-05-25 | 2026-06-06 | -70 | 2026-06-06 | -82 | NOTICE + SMI |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started | Total |  | No | 5 | 02 | 0107
Unit 5-13-0203 | On Notice | 2026-06-01 | 2026-06-13 | -77 | 2026-06-13 | -89 | NOTICE + SMI |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started | Total |  | No | 5 | 13 | 0203
Unit 5-12-0307 | Vacant ready | 2025-04-01 | 2025-03-28 | 349 |  |  | VACANT | 2025-04-02 | Done | 2025-04-03 | Done | 2025-04-04 | Done | 2025-04-09 | Done | 2025-04-10 | Done | Total | yes | No | 5 | 12 | 0307
Unit 5-18-0116 | Vacant not ready | 2025-04-01 | 2026-02-28 | 349 |  |  | VACANT | 2025-04-02 | Done | 2025-04-03 | Done | 2025-04-04 | Done | 2025-04-09 | Done | 2025-04-10 | Done | Total | yes | No | 5 | 18 | 0116 | [ISSUE:Wether ¦ weather storm freezes]
Unit 5-18-0238 | Vacant ready | 2025-06-09 | 2025-06-18 | 280 |  |  | VACANT | 2025-06-10 | Done | 2025-06-11 | Done | 2025-06-12 | Done | 2025-06-17 | Done | 2025-06-18 | Done | Total | yes | No | 5 | 18 | 0238
Unit 8-01-3001 | Vacant ready | 2025-07-08 | 2025-07-22 | 251 |  |  | VACANT | 2025-07-09 | Done | 2025-07-10 | Done | 2025-07-11 | Done | 2025-07-16 | Done | 2025-07-17 | Done | Michael | yes | No | 8 | 01 | 3001
Unit 5-18-0422 | Vacant ready | 2025-07-31 | 2025-11-24 | 228 |  |  | VACANT | 2025-08-01 | Done | 2025-08-04 | Done | 2025-08-05 | Done | 2025-08-08 | Done | 2025-08-11 | Done | Total | yes | No | 5 | 18 | 0422
Unit 8-01-2001 | Vacant ready | 2025-09-14 | 2025-09-25 | 183 |  |  | VACANT | 2025-09-15 | Done | 2025-09-16 | Done | 2025-09-17 | Done | 2025-09-22 | Done | 2025-09-23 | Done | Michael | yes | No | 8 | 01 | 2001
Unit 5-15-0305 | Vacant ready | 2025-10-09 | 2025-12-11 | 158 |  |  | VACANT | 2025-10-10 | Done | 2025-10-13 | Done | 2025-10-14 | Done | 2025-10-17 | Done | 2025-10-20 | Done | Total | yes | No | 5 | 15 | 0305
Unit 5-18-0202 | Vacant ready | 2025-11-10 | 2025-12-12 | 126 |  |  | VACANT | 2025-11-11 | Done | 2025-11-12 | Done | 2025-11-13 | Done | 2025-11-18 | Done | 2025-11-19 | Done | Total | yes | No | 5 | 18 | 0202
Unit 7-10-0303 | Vacant ready | 2025-11-11 | 2025-12-26 | 125 |  |  | VACANT | 2025-11-12 | Done | 2025-11-13 | Done | 2025-11-14 | Done | 2025-11-19 | Done | 2025-11-20 | Done | Brad | yes | No | 7 | 10 | 0303
Unit 8-01-3013 | Vacant ready | 2025-11-12 | 2025-12-10 | 124 |  |  | VACANT | 2025-11-13 | Done | 2025-11-14 | Done | 2025-11-17 | Done | 2025-11-20 | Done | 2025-11-21 | Done | Michael | yes | No | 8 | 01 | 3013
Unit 5-17-0119 | Vacant ready | 2025-12-05 | 2025-12-26 | 101 |  |  | VACANT | 2025-12-08 | Done | 2025-12-09 | Done | 2025-12-10 | Done | 2025-12-15 | Done | 2025-12-16 | Done | Total | yes | No | 5 | 17 | 0119
Unit 7-11-0315 | Vacant ready | 2025-12-11 | 2026-01-07 | 95 |  |  | VACANT | 2025-12-12 | Done | 2025-12-15 | Done | 2025-12-16 | Done | 2025-12-19 | Done | 2025-12-22 | Done | Brad | yes | No | 7 | 11 | 0315
Unit 5-02-0109 | Vacant ready | 2025-12-25 | 2026-01-16 | 81 |  |  | VACANT | 2025-12-26 | Done | 2025-12-29 | Done | 2025-12-30 | Done | 2026-01-02 | Done | 2026-01-05 | Done | Total | yes | No | 5 | 02 | 0109
Unit 7-04-0303 | Vacant ready | 2025-12-30 | 2026-01-16 | 76 |  |  | VACANT | 2025-12-31 | Done | 2026-01-01 | Done | 2026-01-02 | Done | 2026-01-07 | Done | 2026-01-08 | Done | Brad | yes | No | 7 | 04 | 0303
Unit 7-02-0302 | Vacant ready | 2026-01-02 | 2026-01-16 | 73 |  |  | VACANT | 2026-01-05 | Done | 2026-01-06 | Done | 2026-01-07 | Done | 2026-01-12 | Done | 2026-01-13 | Done | Miguel G | yes | No | 7 | 02 | 0302
Unit 7-06-0106 | Vacant ready | 2026-01-05 | 2026-01-19 | 70 |  |  | VACANT | 2026-01-06 | Done | 2026-01-07 | Done | 2026-01-08 | Done | 2026-01-13 | Done | 2026-01-14 | Done | Brad | Yes | No | 7 | 06 | 0106
Unit 7-11-0318 | Vacant ready | 2026-01-07 | 2026-01-26 | 68 |  |  | VACANT | 2026-01-08 | Done | 2026-01-09 | Done | 2026-01-12 | Done | 2026-01-15 | Done | 2026-01-16 | Done | Brad | Yes stack | No | 7 | 11 | 0318
Unit 5-18-0218 | Vacant ready | 2026-01-15 | 2026-02-06 | 60 |  |  | VACANT | 2026-01-16 | Done | 2026-01-19 | Done | 2026-01-20 | Done | 2026-01-23 | Done | 2026-01-26 | Done | Total | Yes stack | No | 5 | 18 | 0218
Unit 7-10-0302 | Vacant ready | 2026-01-16 | 2026-02-06 | 59 |  |  | VACANT | 2026-01-19 | Done | 2026-01-20 | Done | 2026-01-21 | Done | 2026-01-26 | Done | 2026-01-27 | Done | Miguel G | Yes | No | 7 | 10 | 0302
Unit 5-17-0215 | Vacant ready | 2026-01-16 | 2026-02-13 | 59 |  |  | VACANT | 2026-01-19 | Done | 2026-01-20 | Done | 2026-01-21 | Done | 2026-01-26 | In Progress | 2026-01-27 | In Progress | Total | Yes | No | 5 | 17 | 0215
Unit 5-17-0311 | Vacant ready | 2026-01-17 | 2026-02-06 | 58 |  |  | VACANT | 2026-01-19 | Done | 2026-01-20 | Done | 2026-01-21 | Done | 2026-01-26 | Done | 2026-01-27 | Done | Total | Yes | No | 5 | 17 | 0311
Unit 8-01-3086 | Vacant ready | 2026-01-18 | 2026-01-31 | 57 |  |  | VACANT | 2026-01-19 | Done | 2026-01-20 | Done | 2026-01-21 | Done | 2026-01-26 | Done | 2026-01-27 | Done | Michael | yes | No | 8 | 01 | 3086
Unit 8-01-2083 | Vacant ready | 2026-01-21 | 2026-02-04 | 54 |  |  | VACANT | 2026-01-22 | Done | 2026-01-23 | Done | 2026-01-26 | Done | 2026-01-29 | Done | 2026-01-30 | Done | Brad | Yes | No | 8 | 01 | 2083
Unit 5-17-0310 | Vacant ready | 2026-01-22 | 2026-02-02 | 53 |  |  | VACANT | 2026-01-23 | Done | 2026-01-26 | Done | 2026-01-27 | Done | 2026-01-30 | Done | 2026-02-02 | Done | Total | Yes | No | 5 | 17 | 0310
Unit 7-02-0116 | Vacant ready | 2026-01-24 | 2026-02-04 | 51 |  |  | VACANT | 2026-01-26 | Done | 2026-01-27 | Done | 2026-01-28 | Done | 2026-02-02 | Done | 2026-02-03 | Done | Brad | Yes | No | 7 | 02 | 0116
Unit 7-TH1-0104 | Vacant ready | 2026-01-26 | 2026-02-06 | 49 |  |  | VACANT | 2026-01-27 | Done | 2026-01-28 | Done | 2026-01-29 | Done | 2026-02-03 | Done | 2026-02-04 | Done | Brad | Yes stack | No | 7 | TH1 | 0104
Unit 8-01-2034 | Vacant ready | 2026-01-26 | 2026-02-06 | 49 |  |  | VACANT | 2026-01-27 | Done | 2026-01-28 | Done | 2026-01-29 | Done | 2026-02-03 | Done | 2026-02-04 | Done | Michael | Yes | No | 8 | 01 | 2034
Unit 5-18-0346 | Vacant ready | 2026-02-02 | 2026-02-12 | 42 |  |  | VACANT | 2026-02-03 | Done | 2026-02-04 | Done | 2026-02-05 | Done | 2026-02-10 | Done | 2026-02-11 | Done | Total | Yes | No | 5 | 18 | 0346
Unit 7-02-0201 | Vacant ready | 2026-02-07 | 2026-02-17 | 37 |  |  | VACANT | 2026-02-09 | Done | 2026-02-10 | Done | 2026-02-11 | Done | 2026-02-16 | Done | 2026-02-17 | Done | Miguel G | Yes | No | 7 | 02 | 0201
Unit 8-01-2041 | Vacant ready | 2026-02-07 | 2026-02-17 | 37 |  |  | VACANT | 2026-02-09 | Done | 2026-02-10 | Done | 2026-02-11 | Done | 2026-02-16 | Done | 2026-02-17 | Done | Miguel G | Yes | No | 8 | 01 | 2041
Unit 5-18-0310 | Vacant ready | 2026-02-07 | 2026-02-17 | 37 |  |  | VACANT | 2026-02-09 | Done | 2026-02-10 | Done | 2026-02-11 | Done | 2026-02-16 | Done | 2026-02-17 | Done | Total | No | No | 5 | 18 | 0310
Unit 8-01-3107 | Vacant ready | 2026-02-08 | 2026-02-18 | 36 |  |  | VACANT | 2026-02-09 | Done | 2026-02-10 | Done | 2026-02-11 | Done | 2026-02-16 | Done | 2026-02-17 | Done | Miguel G | Yes | No | 8 | 01 | 3107
Unit 7-10-0306 | Vacant ready | 2026-02-09 | 2026-02-19 | 35 |  |  | VACANT | 2026-02-10 | Done | 2026-02-11 | Done | 2026-02-12 | Done | 2026-02-17 | Done | 2026-02-18 | Done | Miguel G | Yes stack | No | 7 | 10 | 0306
Unit 5-11-0303 | Vacant ready | 2026-02-12 | 2026-02-22 | 32 |  |  | VACANT | 2026-02-13 | Done | 2026-02-16 | In Progress | 2026-02-17 | In Progress | 2026-02-20 | In Progress | 2026-02-23 | Scheduled | Total | Yes | No | 5 | 11 | 0303
Unit 7-10-0107 | Vacant not ready | 2026-02-15 | 2026-02-25 | 29 |  |  | VACANT | 2026-02-16 | Done | 2026-02-17 | In Progress | 2026-02-18 | Scheduled | 2026-02-23 | In Progress | 2026-02-24 | Done | Miguel G | Yes stack | No | 7 | 10 | 0107
Unit 7-06-0209 | Vacant not ready | 2026-02-16 | 2026-03-03 | 28 |  |  | VACANT | 2026-02-17 | Done | 2026-02-18 | In Progress | 2026-02-19 | Scheduled | 2026-02-24 | In Progress | 2026-02-25 | Scheduled | Miguel G | Yes | No | 7 | 06 | 0209
Unit 5-10-0203 | Vacant ready | 2026-02-18 | 2026-02-28 | 26 |  |  | VACANT | 2026-02-19 | Done | 2026-02-20 | Scheduled | 2026-02-23 | Scheduled | 2026-02-26 | Scheduled | 2026-02-27 | Scheduled | Total | No | No | 5 | 10 | 0203 | blind 23 inch missing 47 inch blind
Unit 5-17-0104 | Vacant not ready | 2026-02-18 | 2026-02-28 | 26 |  |  | VACANT | 2026-02-19 | Done | 2026-02-20 | Scheduled | 2026-02-23 | Scheduled | 2026-02-26 | Scheduled | 2026-02-27 | Scheduled | Total | Yes | No | 5 | 17 | 0104 | [ISSUE:Wether ¦ weather storm freezes]
Unit 7-09-0103 | Vacant not ready | 2026-02-18 | 2026-03-05 | 26 |  |  | VACANT | 2026-02-19 | Done | 2026-02-20 | Scheduled | 2026-02-23 | Scheduled | 2026-02-26 | Scheduled | 2026-02-27 | Scheduled | Miguel G | Yes stack | No | 7 | 09 | 0103
Unit 7-07-0107 | Vacant not ready | 2026-02-25 | 2026-03-05 | 19 |  |  | VACANT | 2026-02-26 | Scheduled | 2026-02-27 | Scheduled | 2026-03-02 | Scheduled | 2026-03-05 | Scheduled | 2026-03-06 | Scheduled | Brad |  | No | 7 | 07 | 0107
Unit 7-10-0203 | Vacant not ready | 2026-02-28 | 2026-03-08 | 16 |  |  | VACANT | 2026-03-02 | Scheduled | 2026-03-03 | Scheduled | 2026-03-04 | Scheduled | 2026-03-09 | Scheduled | 2026-03-10 | Scheduled | Brad |  | No | 7 | 10 | 0203
Unit 8-01-1001 | Vacant not ready | 2026-03-01 | 2026-03-14 | 15 |  |  | VACANT | 2026-03-02 | Scheduled | 2026-03-03 | Scheduled | 2026-03-04 | Scheduled | 2026-03-09 | Scheduled | 2026-03-10 | Scheduled | Brad |  | No | 8 | 01 | 1001
Unit 8-01-2011 | Vacant not ready | 2026-03-01 | 2026-03-14 | 15 |  |  | VACANT | 2026-03-02 | Scheduled | 2026-03-03 | Scheduled | 2026-03-04 | Scheduled | 2026-03-09 | Scheduled | 2026-03-10 | Scheduled | Brad |  | No | 8 | 01 | 2011
Unit 5-18-0439 | Vacant not ready | 2026-03-02 | 2026-03-14 | 14 |  |  | VACANT | 2026-03-03 | Scheduled | 2026-03-04 | Scheduled | 2026-03-05 | Scheduled | 2026-03-10 | Scheduled | 2026-03-11 | Scheduled | Total |  | No | 5 | 18 | 0439
Unit 7-02-0207 | Vacant not ready | 2026-03-02 | 2026-03-14 | 14 |  |  | VACANT | 2026-03-03 | Scheduled | 2026-03-04 | Scheduled | 2026-03-05 | Scheduled | 2026-03-10 | Scheduled | 2026-03-11 | Scheduled | Michael |  | No | 7 | 02 | 0207
Unit 8-01-3093 | Vacant not ready | 2026-03-03 | 2026-03-18 | 13 |  |  | VACANT | 2026-03-04 | Scheduled | 2026-03-05 | Scheduled | 2026-03-06 | Scheduled | 2026-03-11 | Scheduled | 2026-03-12 | Scheduled | Brad |  | No | 8 | 01 | 3093
Unit 7-04-0305 | Vacant not ready | 2026-03-04 | 2026-03-14 | 12 |  |  | VACANT | 2026-03-05 | Scheduled | 2026-03-06 | Scheduled | 2026-03-09 | Scheduled | 2026-03-12 | Scheduled | 2026-03-13 | Scheduled | Brad |  | No | 7 | 04 | 0305
Unit 5-03-0327 | Vacant not ready | 2026-03-04 | 2026-03-18 | 12 |  |  | VACANT | 2026-03-05 | Scheduled | 2026-03-06 | Scheduled | 2026-03-09 | Scheduled | 2026-03-12 | Scheduled | 2026-03-13 | Scheduled | Total |  | No | 5 | 03 | 0327
Unit 7-04-0311 | Vacant not ready | 2026-03-06 | 2026-03-16 | 10 |  |  | VACANT | 2026-03-09 | Scheduled | 2026-03-10 | Scheduled | 2026-03-11 | Scheduled | 2026-03-16 | Scheduled | 2026-03-17 | Scheduled | Brad |  | No | 7 | 04 | 0311
Unit 7-10-0101 | Vacant not ready | 2026-03-09 | 2026-03-21 | 7 |  |  | VACANT | 2026-03-10 | Scheduled | 2026-03-11 | Scheduled | 2026-03-12 | Scheduled | 2026-03-17 | Scheduled | 2026-03-18 | Scheduled | Brad |  | No | 7 | 10 | 0101
Unit 7-TH1-0102 | Vacant not ready | 2026-03-09 | 2026-03-21 | 7 |  |  | VACANT | 2026-03-10 | Scheduled | 2026-03-11 | Scheduled | 2026-03-12 | Scheduled | 2026-03-17 | Scheduled | 2026-03-18 | Scheduled | Brad |  | No | 7 | TH1 | 0102
Unit 7-th2-0101 | Vacant not ready | 2026-03-09 | 2026-03-21 | 7 |  |  | VACANT | 2026-03-10 | Scheduled | 2026-03-11 | Scheduled | 2026-03-12 | Scheduled | 2026-03-17 | Scheduled | 2026-03-18 | Scheduled | Michael |  | No | 7 | th2 | 0101
Unit 7-TH2-0101 | Vacant not ready | 2026-03-09 | 2026-03-21 | 7 |  |  | VACANT | 2026-03-10 | Scheduled | 2026-03-11 | Scheduled | 2026-03-12 | Scheduled | 2026-03-17 | Scheduled | 2026-03-18 | Scheduled | Michael |  | No | 7 | TH2 | 0101
Unit 7-03-0304 | On Notice | 2026-03-10 | 2026-03-24 | 6 |  |  | VACANT |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started | Brad |  | No | 7 | 03 | 0304
Unit 8-01-3030 | On Notice | 2026-03-11 | 2026-03-25 | 5 |  |  | VACANT |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started | Michael |  | No | 8 | 01 | 3030
Unit 5-17-0108 | On Notice | 2026-03-11 | 2026-03-25 | 5 |  |  | VACANT |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started | Total |  | No | 5 | 17 | 0108
Unit 5-13-0305 | On Notice | 2026-03-17 | 2026-03-31 | -1 |  |  | NOTICE |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started | Total |  | No | 5 | 13 | 0305
Unit 5-12-0303 | On Notice | 2026-03-18 | 2026-04-01 | -2 |  |  | NOTICE |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started | Total |  | No | 5 | 12 | 0303
Unit 5-18-0221 | On Notice | 2026-03-18 | 2026-04-01 | -2 |  |  | NOTICE |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started | Total |  | No | 5 | 18 | 0221
Unit 8-01-3083 | On Notice | 2026-03-21 | 2026-04-04 | -5 |  |  | NOTICE |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started | Michael |  | No | 8 | 01 | 3083
Unit 5-17-0316 | On Notice | 2026-03-22 | 2026-04-04 | -6 |  |  | NOTICE |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started | Total |  | No | 5 | 17 | 0316
Unit 8-01-1089 | On Notice | 2026-03-23 | 2026-04-04 | -7 |  |  | NOTICE |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started | Michael |  | No | 8 | 01 | 1089
Unit 8-01-2035 | On Notice | 2026-03-27 | 2026-04-10 | -11 |  |  | NOTICE |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  |  | No | 8 | 01 | 2035
Unit 8-01-3053 | On Notice | 2026-03-28 | 2026-04-11 | -12 |  |  | NOTICE |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  |  | No | 8 | 01 | 3053
Unit 8-01-4051 | On Notice | 2026-03-30 | 2026-04-11 | -14 |  |  | NOTICE |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started | Michael |  | No | 8 | 01 | 4051
Unit 8-01-4080 | On Notice | 2026-03-30 | 2026-04-11 | -14 |  |  | NOTICE |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  |  | No | 8 | 01 | 4080
Unit 8-01-4124 | On Notice | 2026-03-31 | 2026-04-14 | -15 |  |  | NOTICE |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started | Michael |  | No | 8 | 01 | 4124
Unit 5-01-0206 | On Notice | 2026-04-01 | 2026-04-15 | -16 |  |  | NOTICE |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started | Total |  | No | 5 | 01 | 0206
Unit 7-08-0306 | On Notice | 2026-04-02 | 2026-04-16 | -17 |  |  | NOTICE |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started | Brad |  | No | 7 | 08 | 0306
Unit 7-08-0203 | On Notice | 2026-04-04 | 2026-04-18 | -19 |  |  | NOTICE |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  |  | No | 7 | 08 | 0203
Unit 5-10-0302 | On Notice | 2026-04-06 | 2026-04-18 | -21 |  |  | NOTICE |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started | Total |  | No | 5 | 10 | 0302
Unit 7-09-0109 | On Notice | 2026-04-07 | 2026-04-21 | -22 |  |  | NOTICE |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  |  | No | 7 | 09 | 0109
Unit 8-01-1122 | On Notice | 2026-04-07 | 2026-04-21 | -22 |  |  | NOTICE |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started | Michael |  | No | 8 | 01 | 1122
Unit 8-01-2010 | On Notice | 2026-04-07 | 2026-04-21 | -22 |  |  | NOTICE |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started | Michael |  | No | 8 | 01 | 2010
Unit 8-01-2053 | On Notice | 2026-04-07 | 2026-04-21 | -22 |  |  | NOTICE |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started | Michael |  | No | 8 | 01 | 2053
Unit 7-03-0308 | On Notice | 2026-04-10 | 2026-04-24 | -25 |  |  | NOTICE |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started | Brad |  | No | 7 | 03 | 0308
Unit 5-17-0118 | On Notice | 2026-04-11 | 2026-04-25 | -26 |  |  | NOTICE |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started | Total |  | No | 5 | 17 | 0118
Unit 5-15-0205 | On Notice | 2026-04-14 | 2026-04-28 | -29 |  |  | NOTICE |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started | Total |  | No | 5 | 15 | 0205
Unit 5-17-0209 | On Notice | 2026-04-14 | 2026-04-28 | -29 |  |  | NOTICE |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started | Total |  | No | 5 | 17 | 0209
Unit 5-18-0106 | On Notice | 2026-04-14 | 2026-04-28 | -29 |  |  | NOTICE |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started | Total |  | No | 5 | 18 | 0106
Unit 5-18-0240 | On Notice | 2026-04-14 | 2026-04-28 | -29 |  |  | NOTICE |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started | Total |  | No | 5 | 18 | 0240
Unit 8-01-3011 | On Notice | 2026-04-16 | 2026-04-30 | -31 |  |  | NOTICE |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  |  | No | 8 | 01 | 3011
Unit 8-01-4017 | On Notice | 2026-04-19 | 2026-05-02 | -34 |  |  | NOTICE |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started | Michael |  | No | 8 | 01 | 4017
Unit 7-04-0308 | On Notice | 2026-04-19 | 2026-05-02 | -34 |  |  | NOTICE |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  |  | No | 7 | 04 | 0308
Unit 5-10-0303 | On Notice | 2026-04-21 | 2026-05-05 | -36 |  |  | NOTICE |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started | Total |  | No | 5 | 10 | 0303
Unit 5-16-0203 | On Notice | 2026-04-23 | 2026-05-07 | -38 |  |  | NOTICE |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started | Total |  | No | 5 | 16 | 0203
Unit 8-01-2045 | On Notice | 2026-04-23 | 2026-05-07 | -38 |  |  | NOTICE |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  |  | No | 8 | 01 | 2045
Unit 7-10-0301 | On Notice | 2026-04-26 | 2026-05-09 | -41 |  |  | NOTICE |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  |  | No | 7 | 10 | 0301
Unit 7-03-0118 | On Notice | 2026-04-27 | 2026-05-09 | -42 |  |  | NOTICE |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started | Brad |  | No | 7 | 03 | 0118
Unit 8-01-4013 | On Notice | 2026-04-27 | 2026-05-09 | -42 |  |  | NOTICE |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  |  | No | 8 | 01 | 4013
Unit 7-11-0317 | On Notice | 2026-04-27 | 2026-05-09 | -42 |  |  | NOTICE |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  |  | No | 7 | 11 | 0317
Unit 8-01-4087 | On Notice | 2026-04-27 | 2026-05-09 | -42 |  |  | NOTICE |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  |  | No | 8 | 01 | 4087
Unit 8-01-2094 | On Notice | 2026-04-28 | 2026-05-12 | -43 |  |  | NOTICE |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started | Michael |  | No | 8 | 01 | 2094
Unit 5-13-0307 | On Notice | 2026-04-28 | 2026-05-12 | -43 |  |  | NOTICE |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started | Total |  | No | 5 | 13 | 0307
Unit 5-17-0101 | On Notice | 2026-04-29 | 2026-05-13 | -44 |  |  | NOTICE |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started | Total |  | No | 5 | 17 | 0101
Unit 7-11-0202 | On Notice | 2026-05-11 | 2026-05-23 | -56 |  |  | NOTICE |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started | Brad |  | No | 7 | 11 | 0202
Unit 7-07-0209 | On Notice | 2026-05-22 | 2026-06-05 | -67 |  |  | NOTICE |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  |  | No | 7 | 07 | 0209
Unit 7-04-0201 | On Notice | 2026-06-01 | 2026-06-13 | -77 |  |  | NOTICE |  | Not Started |  | Not Started |  | Not Started |  | Not Started |  | Not Started | Brad |  | No | 7 | 04 | 0201
Unit 5-03-0327 | On Notice | 2026-03-04 | 2026-03-18 | 12 |  |  | VACANT | [13 empty] | 5 | 03 | 0327
Unit 8-01-3053 | On Notice | 2026-03-28 | 2026-04-11 | -12 |  |  | NOTICE | [13 empty] | 8 | 01 | 3053
Unit 8-01-3011 | On Notice | 2026-04-16 | 2026-04-30 | -31 |  |  | NOTICE | [13 empty] | 8 | 01 | 3011
Unit 5-17-0101 | On Notice | 2026-04-29 | 2026-05-13 | -44 |  |  | NOTICE | [13 empty] | 5 | 17 | 0101
Unit 7-09-0111 | Vacant ready | 2026-01-04 | 2026-01-19 | 71 |  |  | VACANT | [13 empty] | 7 | 09 | 0111
Unit 7-11-0407 | On Notice | 2026-03-28 | 2026-04-11 | -12 |  |  | NOTICE | [13 empty] | 7 | 11 | 0407
Unit 5-03-0230 | On Notice | 2026-04-14 | 2026-04-28 | -29 |  |  | NOTICE | [13 empty] | 5 | 03 | 0230
Unit 5-16-0207 | On Notice | 2026-04-16 | 2026-04-30 | -31 |  |  | NOTICE | [13 empty] | 5 | 16 | 0207
Unit 8-01-1120 | On Notice | 2026-04-20 | 2026-05-02 | -35 |  |  | NOTICE | [13 empty] | 8 | 01 | 1120
Unit 8-01-4037 | On Notice | 2026-04-24 | 2026-05-08 | -39 |  |  | NOTICE | [13 empty] | 8 | 01 | 4037
Unit 7-03-0213 | On Notice | 2026-05-03 | 2026-05-16 | -48 |  |  | NOTICE | [13 empty] | 7 | 03 | 0213
Unit 8-01-3035 | On Notice | 2026-05-04 | 2026-05-16 | -49 |  |  | NOTICE | [13 empty] | 8 | 01 | 3035
Unit 8-01-3114 | On Notice | 2026-05-06 | 2026-05-20 | -51 |  |  | NOTICE | [13 empty] | 8 | 01 | 3114
Unit 5-02-0214 | On Notice | 2026-05-08 | 2026-05-22 | -53 |  |  | NOTICE | [13 empty] | 5 | 02 | 0214
Unit 7-03-0310 | On Notice | 2026-05-12 | 2026-05-26 | -57 |  |  | NOTICE | [13 empty] | 7 | 03 | 0310
Unit 7-11-0212 | On Notice | 2026-05-15 | 2026-05-29 | -60 |  |  | NOTICE | [13 empty] | 7 | 11 | 0212
Unit 5-18-0114 | On Notice | 2026-05-25 | 2026-06-06 | -70 |  |  | NOTICE | [13 empty] | 5 | 18 | 0114
Formulas:
DV = IF(DMRB5[[#This Row],[Move_out ]]="","",TODAY()-DMRB5[[#This Row],[Move_out ]])
DTBR = IF(DMRB5[[#This Row],[Move_in]]="","",TODAY()-DMRB5[[#This Row],[Move_in]])
Insp = IF(DMRB5[[#This Row],[Move_out ]]="","", IF(OR(DMRB5[[#This Row],[Insp_status ]]="In Progress",DMRB5[[#This Row],[Insp_status ]]="Done", DMRB5[[#This Row],[Insp_status ]]="Scheduled"), WORKDAY(DMRB5[[#This Row],[Move_out ]],1), ""))
Paint = IF(DMRB5[[#This Row],[Move_out ]]="","", IF(OR(DMRB5[[#This Row],[Paint_status]]="In Progress",DMRB5[[#This Row],[Paint_status]]="Done", DMRB5[[#This Row],[Paint_status]]="Scheduled"), WORKDAY(DMRB5[[#This Row],[Move_out ]],2), ""))
MR = IF(DMRB5[[#This Row],[Move_out ]]="","", IF(OR(DMRB5[[#This Row],[MR_Status]]="In Progress",DMRB5[[#This Row],[MR_Status]]="Done", DMRB5[[#This Row],[MR_Status]]="Scheduled"), WORKDAY(DMRB5[[#This Row],[Move_out ]],3), ""))
HK = IF(DMRB5[[#This Row],[Move_out ]]="","", IF(OR(DMRB5[[#This Row],[HK_Status]]="In Progress",DMRB5[[#This Row],[HK_Status]]="Done", DMRB5[[#This Row],[HK_Status]]="Scheduled"), WORKDAY(DMRB5[[#This Row],[Move_out ]],6), ""))
CC = IF(DMRB5[[#This Row],[Move_out ]]="","", IF(OR(DMRB5[[#This Row],[CC_status]]="In Progress",DMRB5[[#This Row],[CC_status]]="Done", DMRB5[[#This Row],[CC_status]]="Scheduled"), WORKDAY(DMRB5[[#This Row],[Move_out ]],7), ""))

## Engine
#VALUE! | #VALUE! | #VALUE!

## Dashboard
Status | Phases | Alert | Vacant Units Overview | Status | Phases | Alert | Walking Path |  | Unit Search ------>>>>> | 0 | Status | Phases | Age Report
Vacant | All | All |  | Vacant | All | All |  |  |  |  | Vacant not ready | All
#VALUE! |  |  |  | #VALUE! |  |  |  | #VALUE! |  |  | #VALUE!
#VALUE!

## Data_Validation
Trafomers | Data | Trafomers | Data | TS | Status | Move ins | W/D | Assign | Status apt | PH | QC
|  |  |  | Done | Vacant ready | today ,this week | Yes | Michael | Vacant ready | 5 | Done
|  |  |  | In Progress | Vacant not ready | next week | Yes stack | Brad | Vacant | 7 | No
|  |  |  | Not Started | On Notice | next month | No | Miguel A | Vacant not ready | 8
|  |  |  | Scheduled |  |  |  | Miguel G | On Notice | All
|  |  |  | Blocked |  |  |  | All | All
Total
Alert
All
Move-in risk
Qc hold
Work stalled
Needs attention
Scheduled to move in
On notice - scheduled
On notice
In progress
Pending start
Apartment ready
Out of scope